# Northwind Therapeutics, Inc.

## Post-Acquisition Integration Status Memorandum

Prepared for the Operating Committee. This memorandum summarises the integration position of the three bolt-on acquisitions completed since 2021 and the open decisions carried into FY2026.

## Position by entity

| Entity | Acquired | Integration state | Open decision |
| --- | --- | --- | --- |
| Calder Pharma | 2021 | Finance ledgers migrated to SAP; HR, IT and regulatory standalone | Whether to retain Bridgewater as HQ or consolidate into Raleigh |
| Deveron Labs | 2023 | Fully standalone on NetSuite; separate payroll and Veeva tenancy | ERP migration deferred twice; Ohio works agreement requires 60-day consultation |
| Lyle Specialty | 2024 | Standalone on Microsoft Dynamics; separate commercial field force | Retention undertaking blocks regulatory reductions before 31 Dec 2026 |

## Recurring themes

Four parallel month-end close processes; consolidated close of 16 working days against a sponsor target of 8.

No preferred-supplier agreement across 34 professional-services vendors.

Three ERP instances and three payroll systems; single-ERP consolidation scoped at $14M over 26 months and deferred in 2022 and 2024.

Office occupancy averaging 41% against 164,000 sq ft of contracted office space at the three non-manufacturing sites.

FICTIONAL SAMPLE - Northwind Therapeutics is not a real company.